## Sheet1
Nº | Pregunta | Opciones | Respuesta Correcta | Veces Realizada | Errores
1 | During PI planning, Agile Teams estimate user stories using story points. What estimation technique is commonly used to estimate Epics in SAFe? | T-Shirt Sizing Ideal Days Affinity Mapping Planning Poker | T-Shirt Sizing | 0 | 0
2 | What is one method for designing the end-to-end Customer experience? | Journey mapping Whole-product Persona development Feature storming | Journey mapping | 0 | 0
3 | What question helps Product Management in creating a Vision? | What problem(s) will the Solution solve? How many Features have been released to the Customer? Which themes are on the Roadmap? What are the teams' skills? | What problem(s) will the Solution solve? | 0 | 0
4 | What is one method to establish a team's velocity? | Compare the average Story points completed throughout the previous Iterations. Calculate the percentage planned versus actual Stories completed during an Iteration Add the Story points for all the Stories planned for the Iteration Add the Story points for all Features completed in the Iteration | Compare the average Story points completed throughout the previous Iterations. | 0 | 0
5 | What is the primary purpose of the Continuous Exploration (CE) process in SAFe? | Discover, explore new product opportunities and identify emerging business and technical trends Review and prioritize the ART Backlog Integrate and evaluate work products early and often Provide continuous feedback to stakeholders | Discover, explore new product opportunities and identify emerging business and technical trends | 0 | 0
6 | Which tool shows dependencies during PI planning? | ART Planning Board PI Objectives ART PI Risks Board Management Review and Problem-Solving session | ART Planning Board | 0 | 0
7 | What is one influence on Solution and PI Roadmaps? | Market dynamics Customer-centric Features ART capacity Value Streams | Market dynamics | 0 | 0
8 | Which statement describes an owned ART PI Risk? | Someone has taken the responsibility of the risk Nothing more can be done, so if a risk occurs, release may be compromised There is a strategy to adjust the plan as necessary The risk has been addressed and is no longer a concern | Someone has taken the responsibility of the risk | 0 | 0
9 | What is one role of Product Management? | Supporting the team in delivering value Connecting with the Customer Getting it built Managing and prioritizing the Team Backlog | Connecting with the Customer | 0 | 0
10 | After addressing risks during the PI Planning in ART PI Risks, what activity follows? | Confidence vote Management Review and Problem-Solving session Retrospective Team breakouts | Confidence vote | 0 | 0
11 | What is the primary purpose of PO Sync? | To conduct backlog refinement To align with Coach Sync participants on the status of the PI To build PI Objectives and improve alignment To assess progress of the Planning Interval (PI) and adjust scope and priorities as needed | To assess progress of the Planning Interval (PI) and adjust scope and priorities as needed | 0 | 0
12 | What is the recommended format for writing User Stories? | I want..., When..., So that... Given..., When...., Then... As a..., I want..., So that... As a..., When..., Then... | As a..., I want..., So that... | 0 | 0
13 | When explaining why the top 10 Features were chosen for PI Planning, which SAFe Core Value is demonstrated? | Alignment Respect for People Transparency Relentless Improvement | Transparency | 0 | 0
14 | Which statement accurately describes the SAFe backlog model? | Epics are in the Solution Train Backlog Features are in the ART Backlog Capabilities are in the ART Backlog Storie are in the Solution Train Backlog | Features are in the ART Backlog | 0 | 0
15 | What is one anti-pattern of the Inspect and Adapt? | Teams find several problems for the problem solving workshop Product Owners present all of the work in the PI System demo No part of the I&A event goes over its timebox Actionable improvement Features are created | Product Owners present all of the work in the PI System demo | 0 | 0
16 | What is one characteristic of writing effective PI Objectives? | Listing out committed Features Including critical Stories Identifying significant risks Describing the value | Describing the value | 0 | 0
17 | What is one benefit of capacity allocation? | It ensures all Value Streams in the Portfolio are appropriately funded It enables effective time-tracking It prevents different types of backlog items from being compared against each another It allocates developers and testers to an initiative | It prevents different types of backlog items from being compared against each another | 0 | 0
18 | How do Agile Teams carry out Continuous Delivery Pipeline activities during the PI? | They explore during the early Iterations and integrate, deploy, and release during the later Iterations They explore, integrate, and deploy during each Iteration, but release at the end of the PI They explore, integrate, deploy, and release new value during each Iteration tegrating and deploying, and then released in a future PI | They explore, integrate, deploy, and release new value during each Iteration | 0 | 0
19 | What is the main objective of the System Demo in SAFe? | Identify risks and impediments Update the PI Objectives Prepare next Iteration Goals Showcase completed features to stakeholders | Showcase completed features to stakeholders | 0 | 0
20 | When should Agile Teams make time for innovation? | When there are Enabler Stories in the Backlog At a consistent time each day during the Iteration During the Innovation and Planning Iteration Continuously throughout the PI | Continuously throughout the PI | 0 | 0
21 | According to SAFe, what is the recommended first step of Iteration Planning? | Review the prior Iteration Analyze the team backlog Establish capacity Facilitate a confidence vote | Establish capacity | 0 | 0
22 | Which of the following is NOT a good practice when working with Epics? | Assigning them to a single team. Communicating their status to stakeholders. Breaking them down into smaller Features. Tracking their progress through the ART Backlog. | Assigning them to a single team. | 0 | 0
23 | What is one area of task for a Product Owner in managing and prioritizing the team backlog? | Foster Built-In Quality Understand Market forces Support Architectural Runway Share Feedback with the ART | Support Architectural Runway | 0 | 0
24 | The Release Train Engineer (RTE) works with the Product Manager to: | Manage risks Track progress All of the propositions Prioritize features and functionalities | All of the propositions | 0 | 0
25 | During Iteration Review, what is one activity performed by an Agile Team? | Gather Feature requirements from stakeholders Identify opportunities for improvement Modify Iteration Goals Demonstrate a working, tested team increment | Demonstrate a working, tested team increment | 0 | 0
26 | What is one outcome of the Iteration Retrospective? | A plan for upcoming milestones Agreement on Stories for the next Iteration Improvement items in the Team Backlog Identification of dependencies with other teams | Improvement items in the Team Backlog | 0 | 0
27 | Which statement describes the Scaled Agile Framework? | It scales Scrum to multiple Agile Teams It provides guidelines for Project Managers It synchronizes alignment, collaboration, and delivery for large numbers of teams It provides strict guidelines for all daily activities | It synchronizes alignment, collaboration, and delivery for large numbers of teams | 0 | 0
28 | What is the purpose of the Solution Vision in SAFe? | To outline the specific goals for the current Planning Interval (PI) To prioritize the ART backlog To define the team's long-term goals To provide a high-level overview of the product or solution | To provide a high-level overview of the product or solution | 0 | 0
29 | Which role does Product Management work with to prioritize Enablers? | Product Owner Development Manager Solution management System Architect | System Architect | 0 | 0
30 | What is one anti-pattern related to System Demos? | Team demos are accepted in place of a System Demo to avoid redundancy System demo takes more than 15 minutes Different team members conduct the demo each Iteration People from outside the Agile Release Train attend the System Demo | Team demos are accepted in place of a System Demo to avoid redundancy | 0 | 0
31 | What is one way Kanban boards are used in SAFe? | To manage runway cadence To manage WIP limits To manage PI objectives To manage non-functional requirements (NFRs) in the backlog | To manage WIP limits | 0 | 0
32 | The ART Planning board includes the following, other than the team names and iterations? | Features, Stories, Dependencies Deliverables, Features, Dependencies Milestones, Epics, Effort Needed to complete Milestones, Features, Dependencies | Milestones, Features, Dependencies | 0 | 0
33 | Why is the problem-solving workshop more effective than traditional lessons learned documents? | Collaboration over documentation is a key recommendation of the Agile Manifesto It involves a small group of leaders It makes improvements actionable through backlog item for the next PI Workshops are more engaging then document writting | It makes improvements actionable through backlog item for the next PI | 0 | 0
34 | What does SAFe Team Kanban promote? | Collaboration Compliance Leadership Separation of duties | Collaboration | 0 | 0
35 | Who are important attendees to the PI System Demo? | Business Owners Portfolio Management Board Members Feature Owners | Business Owners | 0 | 0
36 | What system delivers a product or service to a Customer? | Kanban System Operational Value Stream Dual Operating System Development Value Stream | Operational Value Stream | 0 | 0
37 | In PI Planning, what is the responsibility of the Product Owner? | To contribute with communicating the Product Vision and Roadmap to the Development Teams To review the Iteration plans To facilitate the planning event To present the Vision to stakeholders | To contribute with communicating the Product Vision and Roadmap to the Development Teams | 0 | 0
38 | Why is it important to establish a definition of done? | To ensure Features provide the expected business benefits To create alignment on when stories are complete To enable Scrum Masters/Team Coaches to enforce quality To create Standardize work between all Agile Teams | To create alignment on when stories are complete | 0 | 0
39 | Which of the following events aligns teams on a train? | PI Planning Iteration Planning PO Sync Coach Sync | PI Planning | 0 | 0
40 | What is the purpose of Iteration Goals? | To align team members to a common purpose To define "the what, the how, and the how much" To set preliminary PI Objectives To identify non-functional requirements | To align team members to a common purpose | 0 | 0
41 | What is one responsibility of the Product Owner during Team Sync? | To relay Customer feedback To add new work into the Iteration To clarify story intent To facilitate event | To clarify story intent | 0 | 0
42 | Which SAFe Core Value is demonstrated when avoid asking teams to commit to their PI Objectives in a sleep-deprived state? | Relentless Improvment Respect for people and culture Alignement Transparency | Respect for people and culture | 0 | 0
43 | What is the main value of the Backlog Refinement? | Team meets with stakeholders to review the deliverables and provide feedback Team commits to a set of goals to be delivered in the Iteration Team reviews and improves its process before the next Iteration Team prepares requirements for Iteration Planning | Team prepares requirements for Iteration Planning | 0 | 0
44 | What is one goal of the Iteration Review? | To add acceptance criteria to Stories in the Iteration To demonstrate completed Stories from the prior PI To receive feedback on the increment To identify dependencies in the backlog | To receive feedback on the increment | 0 | 0
45 | The Product Manager makes weekly visits to a customer's site. Which two Agile Manifesto Values support this behavior? (Choose two.) | Individual interactions over processes and tools Business people and developers must work together daily throughout the project Following a plan over responding to change Working software over detailed documentation Customer collaboration over contract negotiation | Individual interactions over processes and tools | 0 | 0
46 | What is the primary goal of the Innovation and Planning (IP) iteration in SAFe? | Finalize the PI Objectives for the upcoming PI Identify and address technical debt Conduct the Inspect and Adapt (I&A) event Provide dedicated time for exploration and innovation | Provide dedicated time for exploration and innovation | 0 | 0
47 | Where can Product Management find information about when a specific Epic will be completed? | The Development Manager The ART Backlog The Portfolio Backlog The Solution Roadmap | The Portfolio Backlog | 0 | 0
48 | Which statement describes an accepted ART PI Risk? | There is a strategy to adjust the plan as necessary Someone has taken the responsibility of the risk The risk has been addressed and is no longer a concern Nothing more can be done, so if a risk occurs, release may be compromised | Nothing more can be done, so if a risk occurs, release may be compromised | 0 | 0
49 | Which of the following statements is one of the five Lean Thinking principles? | Identify the Value Stream for each product Customer collaboration over contract negotiation Deliver working software frequently Decentralize decision-making | Identify the Value Stream for each product | 0 | 0
50 | Which of the following Agile Manifesto principles aligns with conducing a System Demo? | The best way to convey information is face-to-face conversation Welcome changing requirements, even late in development The team reflects on how to become more effective at regular intervals Working software is the primary measure of progress | Working software is the primary measure of progress | 0 | 0
51 | What element improves when Features and Stories are related to personas? | Compliance Architecture Design Collaboration | Design | 0 | 0
52 | Acceptance criteria provides the details of the story from a testing point of view, and it is created by who? | The team and the Business Owners The team and the Product Owner The Product Owner and Product Management The Release Train Engineer and Product Management | The team and the Product Owner | 0 | 0
53 | How often does the Innovation and planning Iteration (IP) occur? | Once per month Every two PIs Every two Iterations During every PI | During every PI | 0 | 0
54 | What SAFe principle emphasizes delivering the highest value features and solutions early and frequently to customers? | Build incrementally with fast, integrated learning cycles Deliver Value in the shortest sustainable lead time Embrace a Lean-Agile mindset Respect for People and Culture | Build incrementally with fast, integrated learning cycles | 0 | 0
55 | What's the fourth element of the Lean UX Process : Benefit Hypothesis - Collaborative Design - Build MMF? | Alignment Deploy Release Evaluate | Evaluate | 0 | 0
56 | What is the purpose of team backlog refinement in SAFe? | To prepare backlog items for upcoming Iterations To estimate the size of backlog items To groom the backlog with the Scrum Master To prioritize backlog items for the next PI | To prepare backlog items for upcoming Iterations | 0 | 0
57 | What is enabled by the Continuous Delivery Pipeline? | New functionality delivered more frequently A predictable release cadence End-to-end testing Transparent measurements | New functionality delivered more frequently | 0 | 0
58 | What is included in the Inspect and Adapt agenda? | Management review and confidence vote Quantitative and qualitative measurement ART Backlog refinement System Demo | Quantitative and qualitative measurement | 0 | 0
59 | The goal is fast delivery process, ideally requiring little manual effort. What is one capability used to achieve this? | Soft launches Features toggles Non functional requirements Quite releases | Features toggles | 0 | 0
60 | What is essential when communicating the Vision? | The importance of non-functional requirements The importance of Feature prioritizing The importance of Lean budget Guardrails The importance of empathy interviews | The importance of non-functional requirements | 0 | 0
61 | Which Agile Team event supports relentless improvement? | Iteration Planning Backlog refinement Iteration Review Iteration Retrospective | Iteration Retrospective | 0 | 0
62 | Which of the following events shows well the ART is progressing toward meeting the PI objectives? | PI Planning PO Sync Inspect and Adapt Backlog Refinement | PO Sync | 0 | 0
63 | What can assist in facilitating Team Flow? | Test cases Solution Roadmap WIP limits ART Planning Board | WIP limits | 0 | 0
64 | What system convert a business hypothesis into a digitally-enabled solution that delivers customer value? | Customer Journey Value Stream Operational Value Stream Development Value Stream Claims processing Value Stream | Development Value Stream | 0 | 0
65 | Communicating and refining the Vision to the Agile Release Train during PI Planning supports which Core Value? | Alignment Transparency Relentless Improvement Respect for People | Alignment | 0 | 0
66 | What does Kanban board demonstrate? | The accumulated value of team's work A burndown chart of work completed in the Iteration Where a team has too much work-in-process (WIP) The cost of delay of each item on the board | Where a team has too much work-in-process (WIP) | 0 | 0
67 | Which SAFe Lean-Agile Principle supports applying a Set-Based design approach? | Build incrementally with fast, integrated learning cycles Take an economic view Assume variability, preserve options Apply systems thinking | Assume variability, preserve options | 0 | 0
68 | When an Epic meets the Go criteria in a go or no-go decision, where does the Epic move to? | The Value Stream The Portfolio Backlog The Epic Owner Backlog The Continuous Delivery Pipeline | The Portfolio Backlog | 0 | 0
69 | What is defined as a product, service, or system delivered to the customer? | Solution Value Capability Epic | Solution | 0 | 0
70 | What is a common anti-pattern for teams trying to prepare their draft objectives at PI planning? | Remove jargon so that PI Objectives are understandable to Business Owners and Customers Too much time is spent analyzing each Story Describe the value and impact Not using Features or Stories as PI Objectives | Too much time is spent analyzing each Story | 0 | 0
71 | Which of the following types of information is shared between the teams on an ART? | A set of metrics A commitment to business agility A common mission using a single backlog A set of regulations | A common mission using a single backlog | 0 | 0
72 | During PI Planning, which activity happens after "dependencies are resolved and risks are addressed"? | Team breakouts Retrospective Confidence vote Management Review and Problem-Solving session | Confidence vote | 0 | 0
73 | What term characterizes an initiative that requires financial approval before implementation? | Compliance Capability Epic Non-Functional Requirement | Epic | 0 | 0
74 | The goal of the Product Owner is most closely aligned with which Agile Manifesto principle? | Welcome changing requirements, even late in development The highest priority is to satisfy the customer through early and continuous delivery of valuable software Business people and developers must work together daily throughout the project Build projects around motivated individuals | The highest priority is to satisfy the customer through early and continuous delivery of valuable software | 0 | 0
75 | How do Business Owners quantify the value of PI Objectives? | By assigning Story Points By assigning business value By estimating return on investment By totaling the Epic budget | By assigning business value | 0 | 0
76 | Who participates in the PI Planning event in SAFe? | Scrum Masters Release Train Engineers Product Managers All of the propositions DevOps Engineers | All of the propositions | 0 | 0
77 | What is a recommended time horizon of the Planning Interval (PI) Roadmap? | Less then 1 year 2-4 years 2 years More then one year | Less then 1 year | 0 | 0
78 | What is the recommended frequency for conducting Iteration Planning in SAFe? | Every week Every month Every two weeks Every three weeks | Every two weeks | 0 | 0
79 | What is the next action for improvement items identified during the Iteration Retrospective? | They are given to the Scrum Master/Team Coach who resolves them They are entered as Stories in the Team Backlog They are ROAMed with the rest of the risks They are escalated to the Business Owners | They are entered as Stories in the Team Backlog | 0 | 0
80 | What enables flow through the Continuous Delivery Pipeline? | The Solution Vision Cost of delay The ART Kanban Capacity allocation | The ART Kanban | 0 | 0
81 | When is a Story considered complete? | The scope has been changed It is accepted by the Stakeholders The team is done working on it It satisfies the Definition of Done | It satisfies the Definition of Done | 0 | 0
82 | What does the ART planning board show? | Risks Capacity and load Epics Significant dependencies | Significant dependencies | 0 | 0
83 | What is one tool that visualizes Features representing a workflows? | User Experience Design Team Kanban Continuous Delivery Pipeline Story Maps | Story Maps | 0 | 0
84 | Who is responsible for defining and communicating the ART's Vision and Roadmap? | Release Train Engineer (RTE) Business Owners Product Management System Architect | Product Management | 0 | 0
85 | What is one responsibility of the Product Owner? | Estimating Stories Prioritizing the Team Backlog Testing Features Assigning PI Objectives | Prioritizing the Team Backlog | 0 | 0
86 | During PI planning, what is the primary purpose of the Business Context and Content session? | Review and prioritize features Estimate user stories Presents a perspective on how effectively existing solutions are addressing current customer needs. Identify dependencies between Agile Teams | Presents a perspective on how effectively existing solutions are addressing current customer needs. | 0 | 0
87 | Who often participates as the ART's Business Owners to approve the team's PI Objectives? | Product Managers Product Owners System Architects Scrum Masters/Team Coaches | Product Managers | 0 | 0
88 | What work-item can be split from Epics? | Features Spikes Stories Tasks | Features | 0 | 0
89 | On day two of PI Planning, management presents adjustments based on the previous day's management review and problem-solving meeting. What is one possible type of adjustment they could make? | Create new User Stories Change a team's plan Redefine the length of the PI Adjust business priorities | Adjust business priorities | 0 | 0
90 | Which of the following statements is true about the team backlog? | The team backlog is where the team finalizes work The team backlog is where the team commits to work The team backlog is where Stories are accepted The team backlog is where the team refines possible Stories | The team backlog is where the team refines possible Stories | 0 | 0
91 | What is one tool that identifies specific practices for potential improvement? | Flow metrics Objectives and key results Key performance indicators Competency assessments | Competency assessments | 0 | 0
92 | Which role ensures that the ART has the Vision and Backlog needed to engage in PI Planning successfully? | Release Train Engineer Product Management Lean-Agile Center of Excellence Product Owner | Product Management | 0 | 0
93 | What is the recommended duration for a Planning Interval (PI) in SAFe? | 16 to 20 weeks 8 to 12 weeks 12 to 16 weeks 20 to 24 weeks | 8 to 12 weeks | 0 | 0
94 | Which is developed by teams and rolled up to the ART level during PI Planning? | Milestones ART PI Risks PI Objectives Dependencies | PI Objectives | 0 | 0
95 | Which technique is used to discover key Customers, their needs, and align on the product vision in SAFe Product Owner/Product Manager role? | Product Features Impact Mapping Business Model Canvas Customer Journey Mapping | Customer Journey Mapping | 0 | 0
96 | Why do Agile Teams use Iteration Goals? | To hold the team accountable to their PI Objectives To ensure the team accomplishes the committed Stories for each Iteration To align the team members and the Product Owner to a common purpose To summarize the business outcomes an Agile Team intends to achieve during the PI | To align the team members and the Product Owner to a common purpose | 0 | 0
97 | What is one organizing attribute that teams share with the other teams on their ART? | Synchronization to a common cadence Simultaneous release in one pipeline Facilitation techniques amongst all meetings Prioritization across all backlogs | Synchronization to a common cadence | 0 | 0
98 | What is the role of the Product Owner during the Iteration Review? | To demo the new features to stakeholders To review the team's problems and impediments To provide key inputs before, during and after the event To facilitate the iteration planning meeting | To provide key inputs before, during and after the event | 0 | 0
99 | Which SAFe 6 principle emphasizes that Business owners, developers, and customers have a shared responsibility to ensure that investment in new solutions will deliver economic benefits? | Apply systems thinking Unlock the intrinsic motivation of knowledge workers Base milestones on objective evaluation of working systems Decentralize decision-making | Base milestones on objective evaluation of working systems | 0 | 0
100 | What is commonly used to explore new ideas or determine the feasibility of Epics? | Spikes Hackathons Supplier showcases Design thinking | Spikes | 0 | 0
101 | What information do Product Owners communicate to their teams after PO Sync? | Improvement items Risks Impediments Adjustments | Adjustments | 0 | 0
102 | What is one strategy in SAFe 6 for managing complex critical path challenges? | Adjust work between teams or split Features and Stories Distribute work to other teams Sequence work to eliminate same Iteration dependencies Allocate work between teams based on forecasted capacity | Adjust work between teams or split Features and Stories | 0 | 0
103 | True or false : conducting a System Demo is most aligned with "Welcome changing requirements, even late in development" principle of the Agile Manifesto? | True False | False | 0 | 0
104 | What are personas in SAFe? | Key end-users the Product Owner leverages for managing the backlog Fictional characters that act as a representative user when discussing the backlog Strategic stakeholders that influence the backlog External customers that are on the product Roadmap | Fictional characters that act as a representative user when discussing the backlog | 0 | 0
105 | What is the role of the Product Owner during the Iteration Retrospective? | The Product Owner should provide feedback to the team on their progress towards the Product Backlog The Product Owner should not participate in the Iteration Retrospective, as it is a time for the team to reflect on their own work The Product Owner should participate in the Iteration Retrospective, but should not lead it The Product Owner should lead the Iteration Retrospective | The Product Owner should participate in the Iteration Retrospective, but should not lead it | 0 | 0
106 | Which of the following roles has content authority for the ART Backlog? | Product Management System Architect Business Owner Product Owner | Product Management | 0 | 0
107 | How can Product Management leverage market rhythms? | Adjust the delivery of Features to meet market needs Improve PI Planning scheduling Improve Features prioritization Adjust the timing of marketing campaigns | Adjust the delivery of Features to meet market needs | 0 | 0
108 | What is the role of the Product Owner during the System Demo? | To demonstrate the new features to stakeholders To prioritize the features for the next Planning Interval (PI) Helps the team satisfy dependencies, demonstrate incremental value, and maintain cadence with the ART. To facilitate the event and address questions from stakeholders | Helps the team satisfy dependencies, demonstrate incremental value, and maintain cadence with the ART. | 0 | 0
109 | What are the three parts of an Inspect and Adapt event? | PI System Demo, qualitative and quantitative measurement, and problem-solving workshop Problem-solving workshop, actual business value review, and Strategic Theme presentation Actual business value review, root cause analysis, and retrospective Retrospective, qualitative and quantitative measurement, and Strategic Theme presentation | PI System Demo, qualitative and quantitative measurement, and problem-solving workshop | 0 | 0
110 | What is enabled by the key components of the Continuous Delivery Pipeline? | Predictable release cadence Accelerated release of value End-to-end testing Hyper-transparent measurements | Accelerated release of value | 0 | 0
111 | What is the role of the Product Owner during the Backlog Refinement event? | To provide technical guidance to the Agile teams To review and prepare backlog items for upcoming iterations To prioritize the ART backlog To facilitate the event and keep it on track | To review and prepare backlog items for upcoming iterations | 0 | 0
112 | During which event does the team preview and elaborate on upcoming Stories | PI Planning Backlog Refinement Iteration Planning Team Sync | Backlog Refinement | 0 | 0
113 | What is one intended outcome of the problem-solving workshop? | Developing solutions to recognized problems that blocked or slowed work Generating innovative approaches to common issues facing teams and ARTS Forming working groups to better understand issues from the PI Creating improvement backlog items as planned work | Creating improvement backlog items as planned work | 0 | 0
114 | What is one element of the CALMR approach to DevOps? | Create a culture of shared responsibility Commit to accelerated delivery Communicate risk Create a flow of value | Create a culture of shared responsibility | 0 | 0
115 | What is one input to the Vision? | Team topologies Portfolio Backlog Customer feedback Feature context | Customer feedback | 0 | 0
116 | What is the purpose of the ART (Agile Release Train) in SAFe? | To provide a high-level overview of the ART's progress To manage the ART's budget and financials To synchronize the activities of multiple Agile teams To align the program with the organization's strategic goals | To synchronize the activities of multiple Agile teams | 0 | 0
117 | How are Features prioritized in the ART backlog? | By the Product Manger based on the Vision and the Roadmap By the Business Owner based on the program priorities By the Scrum Master based on team capacity By the System Architect based on technical considerations | By the Product Manger based on the Vision and the Roadmap | 0 | 0
118 | What is the recommended Timebox by SAFe for Iteration Review? | As needed 1 to 2 Hours 2 to 3 Hours 3 to 4 Hours | 1 to 2 Hours | 0 | 0
119 | True or False: Epics are estimated in story points rolled up from feature estimates? | False True | True | 0 | 0
120 | What are the minimum requirements for a Feature? | Name, benefit hypothesis, and acceptance criteria Acceptance criteria, data models, and priority Benefit hypothesis, acceptance criteria, and priority Non-functional requirements, data models, and architecture | Name, benefit hypothesis, and acceptance criteria | 0 | 0
121 | During PI planning, who is responsible for leading the discussion about dependencies and risks? | Business Owner Team Coach Release Train Engineer (RTE) Product Owner | Release Train Engineer (RTE) | 0 | 0
122 | Who participates in the Inspect and Adapt (I&A) event in SAFe? | Agile teams and stakeholders Release Train Engineers and Product Management Product Owners and Scrum Masters All the propositions | All the propositions | 0 | 0
123 | Which event allows teams to review the progress of the current Planning Interval (PI)? | System Demo PI Planning Backlog Refinement Sprint Review | System Demo | 0 | 0
124 | What is the relationship between a Product Owner (PO) and a Product Manager (PM)? | The PO identifies market needs, the PM is solution, technology, and team facing The PO is team-oriented, the PM is market-oriented The PO drives PI Objectives, the PM drives Iteration Goals The PO contributes to the ART Backlog, the PM establishes Story acceptance criteria | The PO is team-oriented, the PM is market-oriented | 0 | 0
125 | What is one influence on the Vision? | Lean Budget Guardrails Strategic Themes Portfolio Backlog items Value Stream budgets | Strategic Themes | 0 | 0
126 | Product Management works with which other role to define and maintain nonfunctional requirements? | Portfolio Managers System and Solution Architect / Engineering System Team Lean UX | System and Solution Architect / Engineering | 0 | 0
127 | What is the purpose of the PI Planning event in SAFe? | To prioritize features for the upcoming Planning Interval To present the progress of the Agile Release Train to stakeholders To create a detailed plan for the next iteration To align all Agile teams with the ART's goals and priorities | To align all Agile teams with the ART's goals and priorities | 0 | 0
128 | Where are workflows, activities, and required automation represented? | In the Lean Startup Cycle In the Architectural Runway In the Team Kanban In the Continuous Delivery Pipeline | In the Continuous Delivery Pipeline | 0 | 0
129 | Which of the following is the best way of defining an Epic successfully? | Creating the Lean Business Case All of the propositions Estimating Epic Costs Defining the MVP | All of the propositions | 0 | 0
130 | How are PI Objectives created and communicated in SAFe? | They are created by the Product Owners and the ART during PI Planning They are created by the Business Owners and communicated to the ART during PI Planning They are created collaboratively by the Agile teams and communicated to the ART during PI Planning They are created by the Release Train Engineer (RTE) and communicated to the ART during PI Planning | They are created collaboratively by the Agile teams and communicated to the ART during PI Planning | 0 | 0
131 | What are two primary responsibilities of Business Owners in Planning Interval (PI) Planning? | To assign planned Business Value To establish the PI Budget To create Lean business cases To ensure that team members plan all of their priorities To present the Business Context and Vision | To assign planned Business Value; To present the Business Context and Vision | 0 | 0
132 | What helps visualize work during PI planning? | ART Predictability Measure ART Objectives ART PI Risks ART Planning Board | ART Planning Board | 0 | 0
133 | The team is struggling to agree on the story point sizing of a new user story. The PO was previously a related domain expert and feels the team is wasting time. What is the best decision? | Continue to support the team's decision on sizing Suggest the team stop the sizing of the user story and add it to the next iteration as is Instruct the Scrum Master to resize the story Make the team aware of her expertise and decide the size for them | Continue to support the team's decision on sizing | 0 | 0
134 | What is one SAFe Core Competency? | Agile Product Delivery Built-in Quality Design Thinking Practices Growth Mindset | Agile Product Delivery | 0 | 0
135 | Which SAFe Core Value Helps if decisions pull the organization in different directions, significant delays and quality concerns? | Respect for people Relentless improvement Transparency Alignment | Alignment | 0 | 0
136 | Which concept provides a set of tools that supports the creation of Features? | Customer Centricity Flow Acceleration Agile Quality Design Thinking | Design Thinking | 0 | 0
137 | What is one goal of the Innovation and Planning (IP) iteration? | Use the Built-In Estimation Buffer As Needed To conduct a retrospective To refine the Teams Backlogs To create a Shared Basis for Story Point Estimation | Use the Built-In Estimation Buffer As Needed | 0 | 0
138 | What is one anti-pattern that indicates a team is overcommitting to work? | Team velocity increases over time Team members are pulling in work from future Iterations Flow time is decreasing Capacity and load are exactly the same | Capacity and load are exactly the same | 0 | 0
139 | Which technique helps Product Owners collaborate with Agile Teams and stakeholders to determine the economic impact of potential work items? | Story Points Estimation Kano Model Analysis Feature Prioritization Matrix Cost of Delay | Cost of Delay | 0 | 0
140 | What is one purpose of acceptance criteria? | To capture the necessary steps of the Story To identify how the Story can be validated To explain how the Story will benefit Customers To identify which Customers will benefit from the Story | To identify how the Story can be validated | 0 | 0
141 | What is essential when communicating the PI Roadmap? | Describe how the PI Roadmap supports Design Thinking Describe how the PI Roadmap supports Feature prioritizing Describe how the PI Roadmap supports Lean budget Guardrails Describe how the PI Roadmap supports key Epics and Milestones | Describe how the PI Roadmap supports key Epics and Milestones | 0 | 0
142 | Which event involves teams working on new ideas often added to the ART Kanban? | Supplier showcase Hackathon Coach Sync PI Planning | Hackathon | 0 | 0
143 | Which of the following is an Agile Manifesto principle? | Apply cadence and synchronize with cross-domain planning Working software is the primary measure of progress Base Milestones on objective evaluation of working systems Let the Customer pull value from the producer | Working software is the primary measure of progress | 0 | 0
144 | What is a positive aspect of using PI Objectives? | To promote centralized decisions To achieve commitment from management To obtain immediate feedback from Business Owners To commit to specific Features | To obtain immediate feedback from Business Owners | 0 | 0
145 | When should innovation activities be conducted by teams on the Agile Release Train? | At a consistent time each day during the Iteration Only when innovation Stories rise to the top of the backlog Only during the Innovation and Planning Iteration Throughout the Planning Interval | Throughout the Planning Interval | 0 | 0
146 | What can be revealed during PI Planning? | Opportunity to change Solution Vision Opportunity to release value sooner Opportunity to modify investment strategy Opportunity to update the development value stream | Opportunity to release value sooner | 0 | 0
147 | What does Continuous Exploration help Product Management understand? | Customer needs Solution performance Supplier proposals Release strategy | Customer needs | 0 | 0
148 | The first three elements of the Continuous Delivery Pipeline work together to support delivery of small batches of new functionality. These continuous elements include Exploration, Integration, and what else? | Compliance Deployment Automation Execution | Deployment | 0 | 0
149 | What is the importance of the definition of done? | It creates a clear understanding of when items are complete It prioritizes the work of testers on the team It creates standardized work It provides a way for Scrum Master to enforce quality | It creates a clear understanding of when items are complete | 0 | 0
150 | In the first step of SAFe's Continuous Delivery Pipeline, Product Owners and Product Managers do what activity? | Ensure the Architecture team has sufficient capacity Hypothesize what would create value for Customers Negotiate Supplier contracts Prioritize the Team Backlog | Hypothesize what would create value for Customers | 0 | 0
151 | What is one strategy in SAFe 6 for managing Iteration dependencies challenges? | Distribute work to other teams Adjust work between teams based on forecasted capacity Adjust work sequencing to eliminate same Iteration dependencies Adjust work between teams or split Features and Stories | Adjust work sequencing to eliminate same Iteration dependencies | 0 | 0
152 | What is one main responsibility of Product Management in SAFe? | Defining the team's Definition of Done Defining Product Strategy, Vision and Roadmaps Providing guidance on technical practices Coaching the ART | Defining Product Strategy, Vision and Roadmaps | 0 | 0
153 | Which SAFe principle is most closely aligned with the following statement: "The people closest to the work are the best equipped to make decisions about that work"? | Assume variability, preserve options Decentralize decision-making Apply systems thinking Unlock the intrinsic motivation of knowledge workers | Decentralize decision-making | 0 | 0
154 | Which statement describes a mitigated ART PI Risk? | There is a strategy to adjust the plan as necessary The risk has been addressed and is no longer a concern Some items are simply facts or potential problems that must be understood and accepted Someone has taken the responsibility of the risk | There is a strategy to adjust the plan as necessary | 0 | 0
155 | Which Product Owner responsibility supports the team with value delivery? | Understanding market forces Testing benefit hypothesis Supporting the Architectural Runway Fostering Built-in Quality | Fostering Built-in Quality | 0 | 0
156 | What is one benefit of PI Planning? | It allows leaders to get their objectives planned It ensures teams can work on anything they want It ensures teams do not have dependencies It aligns ART demand to capacity | It aligns ART demand to capacity | 0 | 0
157 | What is one benefit of constant customer feedback? | It reduces the amount of changes to the Features Teams can better align working days with a customer’s schedule It reduces the need for face-to-face collaboration Fast learning cycles | Fast learning cycles | 0 | 0
158 | Where are systems, people who do the work, and the flow of information and materials represented? | Within a Architectural Runway Within a Value Stream Within a Continuous Delivery Pipeline Within a Solution Train | Within a Value Stream | 0 | 0
159 | Epics are decomposed into what? | Features Requirements Enablers Stories | Features | 0 | 0
160 | What is the primary responsibility of a SAFe Product Owner? | Facilitating the PI Planning event Maintaining the ART Kanban board Defining and communicating the ART's Vision and Roadmap Prioritizing the team's backlog | Prioritizing the team's backlog | 0 | 0
161 | What is one way Agile Teams can use an Iteration retrospective to build relentless improvement? | By reviewing team metrics By discussing completed work By reviewing goals and reflecting on what did not happen according to plan By writing improvement Stories | By writing improvement Stories | 0 | 0
162 | Which guideline is an anti pattern for the success of the System Demo? | Make sure only the right participants are present Make sure different team members have the opportunity to demo Team members are not invited to the System Demo to save time Timebox the demo to no more than one hour | Team members are not invited to the System Demo to save time | 0 | 0
163 | Who should attend the PO Sync? | Everyone on the train The Coach Sync participants and the Product Owners The Product Owners, Product Management, and other stakeholders as needed The teams and the RTE | The Product Owners, Product Management, and other stakeholders as needed | 0 | 0
164 | An Agile Release Train (ART) has implemented a completely automated Continuous Integration/Continuous Delivery (CI/CD) pipeline that can deploy code as it is checked into the source-code repository. How might a Product Owner (PO) adjust team events to take advantage of this capability and promote the flow of value? | Release Stories that have been included in the team demo Review and accept Stories as they are completed Implement Feature toggles to control which Stories are released Identify Stories that are cleared for automatic delivery during Iteration Planning | Release Stories that have been included in the team demo | 0 | 0
165 | Which event allows the Agile Teams to showcase their completed features and demonstrate the working solution to stakeholders? | PI Planning Backlog Refinement System Demo Inspect and Adapt (I&A) | System Demo | 0 | 0
166 | Which two types of items are maintained in the Team Backlog? | PI Objectives User Stories Enabler Stories Business Epics Epic Enablers | User Stories; Enabler Stories | 0 | 0
167 | In SAFe, who is responsible for accepting user stories as done? | System Team Scrum Master Product Owner Release Train Engineer (RTE) | Product Owner | 0 | 0
168 | Which of the following questions does a Vision answer? | What problem(s) will the Solution solve? What Solutions are competitors offering? When will the Solution be delivered? What Stories are needed to support it the solution? | What problem(s) will the Solution solve? | 0 | 0
169 | Which statement is true about Weighted Shortest Job First? | It considers the cost of delay and the job size It is equal to the cost of delay The item with the highest cost of delay is prioritized last It identifies specific economic outcomes | It considers the cost of delay and the job size | 0 | 0
170 | When are adjustments made to the initial sequencing of Stories? | At the mid point of the PI At Iteration boundaries During the Team Sync During the PO Sync | At Iteration boundaries | 0 | 0
171 | Which of the following statements is least consistent with the SAFe Core Value of Alignment? | The team should not be allowed to make any decisions without the approval of the Product Owner, even if the decisions are minor and have no impact on the product or the business. The team should be empowered to make decisions, but they should still consult with stakeholders, especially if the decisions have a significant impact on the product or the business. The team should be able to make decisions without consulting with stakeholders, as long as they are aligned with the overall product vision. The Product Owner should be the sole decision-maker for the product, but they should consult with the team and other stakeholders before making any decisions. | The team should not be allowed to make any decisions without the approval of the Product Owner, even if the decisions are minor and have no impact on the product or the business. | 0 | 0
172 | Which SAFe event allows teams to gather and apply the urgent feedback received from the System Demo? | Inspect and Adapt (I&A) Team Demo PI Planning Team Sync | Team Sync | 0 | 0
173 | When prioritizing the backlog, what does taking an economic view mean? | Compare earned value against forecasted value for existing Features Deliver Early and Often With Lean Budget Do not consider sunk costs Use Net Present Value as the leading variable in WSJF | Deliver Early and Often With Lean Budget | 0 | 0
174 | Which SAFe core competency is focused on optimizing the flow of value through the Continuous Delivery Pipeline? | Lean Portfolio Management Organizational Agility Continuous Learning Culture Agile Product Delivery | Agile Product Delivery | 0 | 0
175 | During the Inspect and Adapt (I&A) event, which activity is performed to identify and adress significant issues across multiple ARTs? | Quantitative and Qualitative measurements PI Objectives Review PI System Demo Retrospective and Problem-solving Workshop | Retrospective and Problem-solving Workshop | 0 | 0
176 | Who communicates the Vision during PI Planning? | Product Owner Business Owner System Architect Product Management | Product Management | 0 | 0
177 | Which role is primarily responsible for working with business teams? | Release Train Engineer Enterprise Architect Product Management Product Owner | Product Management | 0 | 0
178 | What unit of time is used on Solution Roadmaps? | Iterations Days PIs Years | Years | 0 | 0
179 | What is the intended value of the Team Sync event? | The team aligns on the progress of Iteration Goals The team reviews and improves processes before the next Iteration The team is able to commit to a set of goals to be delivered in the Iteration The team is able to prepare requirements for Iteration Planning | The team aligns on the progress of Iteration Goals | 0 | 0
180 | Between which two roles the PO provides a crucial link in the bi-directional information flow? | Product Management and Scrum Master Product Management and the Agile team The agile team and Business Owners Product management and Business Owners | Product Management and the Agile team | 0 | 0
181 | What is used to capture the current state of the Portfolio and provide input for defining the future state? | Portfolio Canvas Portfolio Kanban Portfolio Vision Portfolio Backlog | Portfolio Canvas | 0 | 0
182 | What is one of the five basic Agile quality practices applicable to all Agile Teams? | Decentralized decision-making Shift learning left Using non-functional requirements Creating the Architectural Runway | Shift learning left | 0 | 0
183 | What is the first step in Kotter's 8-step process for leading change? | Enlist a volunteer army Build a guiding coalition Generate short-term wins Create a sense of urgency | Create a sense of urgency | 0 | 0
184 | What do Strategic Themes influence directly? | Organization of the ART PI cadence Lean budget Guardrails Enterprise strategy | Lean budget Guardrails | 0 | 0
185 | Which is an aspect of systems thinking? | Mastery drives intrinsic motivation The length of the queue impacts the wait time Cadence makes routine everything that can be routine Optimizing a component does not optimize the system | Optimizing a component does not optimize the system | 0 | 0
186 | What should the team focus on in order to optimize flow? | Requests Delays Sunk costs Costs | Delays | 0 | 0
187 | What is one body of knowledge that informs the SAFe values, principles, mindset, and practices? | Systems thinking Design thinking Lean thinking Customer-centric | Lean thinking | 0 | 0
188 | What is part of the role of Product Management? | To prioritize the ART Backlog To facilitate backlog refinement To define Enablers To assign business value to Features | To prioritize the ART Backlog | 0 | 0
189 | How is the flow of Portfolio Epics managed? | In the ART Backlog In the Portfolio Backlog In the Portfolio Kanban In the ART Kanban | In the Portfolio Kanban | 0 | 0
190 | Which statement correctly describes one aspect of the team's commitment at the end of PI Planning? | A team commits to all the Stories they put on their PI plan A team does not commit to uncommitted objectives A team commits to all the Features they put on the ART planning board A team commits only to the PI Objectives with the highest business value | A team does not commit to uncommitted objectives | 0 | 0
191 | What is one of the Lean budget Guardrails? | Participatory budgeting Spending caps for each ART Continuous Business Owner engagement Objective measurements | Continuous Business Owner engagement | 0 | 0
192 | “Building a problem-sollving culture” is an example of which SAFe Core Value? | Relentless Improvement Transparency Alignment Respect for People | Relentless Improvement | 0 | 0
193 | What is critical to improving flow? | Address the local problems Reduce the batch sizes of work Frequent context switching WIP) (Increase work in process [WIP] limits | Reduce the batch sizes of work | 0 | 0
194 | What is one of the five Lean Thinking principles? | Make value flow without interruptions Responding to change over following a plan Apply systems thinking Working software over comprehensive documentation | Make value flow without interruptions | 0 | 0
195 | What is considered an anti-pattern when assigning business values to team PI Objectives? | High business value is assigned to important Enabler work Business values are assigned to uncommitted objectives Business Owners assign the business value for all teams on the ART All PI Objectives are given a business value of 10 All PI Objectives get value 10 | All PI Objectives get value 10 | 0 | 0
196 | In the ART Kanban some steps have work in process [WIP] limits. Why is this necessary? | To ensure large queues are not forming To reduce handoffs and dependencies To enable Continuous Deployment To support multitasking | To ensure large queues are not forming | 0 | 0
197 | Who has content authority to make decisions at the User Story level during PI Planning? | Scrum Master/Team Coach Agile Team Product Owner Release Train Engineer | Product Owner | 0 | 0
198 | What is the purpose of Customer Centricity? | To build small, partial systems just in time To design custom-built Customer Solutions To understand the Customer's needs To interpret market rhythms | To understand the Customer's needs | 0 | 0
199 | Why is it important to decouple deployment from release? | To allow early access to specific groups of customers To enable releasing functionality on demand to meet business needs To remove the need to respond quickly to production issues To make deploying of assets a business decision | To enable releasing functionality on demand to meet business needs | 0 | 0
200 | Which of the Lean Thinking principles includes the activities from recognizing an opportunity through release and validation? | Precisely specify value by product Pursue perfection Identify the Value Stream for each product Make value flow without interruptions | Identify the Value Stream for each product | 0 | 0
201 | Which of the core competencies of the Lean Enterprise helps align strategy and execution? | Agile Product Delivery Organizational Agility Lean Portfolio Management Team and Technical Agility | Lean Portfolio Management | 0 | 0
202 | Which aspect of leading by example includes modeling desired professional behaviors? | Courage Emotional competence Growing others Authenticity | Authenticity | 0 | 0
203 | What enables enterprises to respond quickly to shifts in the market? | Solution Train Value Stream Business Agility Value Stream Lean Governance Value Stream Customer Segment Value Stream | Business Agility Value Stream | 0 | 0
204 | Which statement best describes Business Agility? | A customer-centric approach to defining, building, and releasing a continuous flow of valuable products and services to customers and users. Applying Lean-Agile principles and practices to the specification, development, deployment, operation, and evolution of the world's largest and most sophisticated systems. The ability to compete and thrive in the digital age by quickly responding to market changes and emerging opportunities with innovative business Solutions. How Lean-thinking people and Agile Teams optimize their business processes, evolve strategy with clear and decisive new commitments, and quickly adapt the organization as needed to capitalize on new opportunities. Compete in digital age | Compete in digital age | 0 | 0
205 | Volume, complexity, knowledge, and uncertainty are all qualities of what? | Cost of Delay Risks WSJF) (Weighted shortest job first [WSJF] Story points | Story points | 0 | 0
206 | What is used to describe functional and non-functional requirements? | Architectural Runway Features Milestones Enablers | Features | 0 | 0
207 | The Lean Thinking principle, “make value flow without interruptions” means identifying what? | Activities that lack innovation Key performance indicators Delays Predictability issues of the train | Delays | 0 | 0
208 | What type of map captures user workflows? | Customer Journey Story Value Stream | Story | 0 | 0
209 | What does the ART planning board show? | Significant dependencies Risks Capacity and load Epics | Significant dependencies | 0 | 0
210 | What is one Design Thinking measure of solution success? | Reliability Sustainability Marketability Scalability | Sustainability | 0 | 0
211 | Which statement is a value from the Agile Manifesto? | Responding to change over following a plan Respect for people and culture Build incrementally with fast, integrated learning cycles Working software is the primary measure of progress | Responding to change over following a plan | 0 | 0
212 | What brings structure to analysis and decision making around Epics? | Portfolio Canvas Portfolio Backlog Portfolio Vision Portfolio Kanban | Portfolio Kanban | 0 | 0
213 | Reviewing the organization's architecture vision during the first day of PI Planning is an example of what SAFe Core Value? | Alignment Respect for People Transparency Relentless Improvement | Alignment | 0 | 0
214 | What is an example of applying cadence-based synchronization in SAFe? | Teams can only release new software on the same day Teams decide their own Iteration length Teams align the start and end dates of their Iterations Teams meet twice every PI to plan and schedule capacity Align iteration dates | Align iteration dates | 0 | 0
215 | What is one component of the Continuous Delivery Pipeline? | Continuous Exploration Continuous Planning Continuous Improvement Continuous Cadence | Continuous Exploration | 0 | 0
216 | What is the biggest benefit of decentralized decision-making? | Removes accountability from leaders Reduces delays Ensures strategic decisions are made collaboratively Improves transparency | Reduces delays | 0 | 0
217 | What is the next step in the SAFe Implementation Roadmap after organizing around value? | Create the implementation plan Enhance the Portfolio Prepare for ART launch Train teams and launch ARTs Create implementation plan | Create implementation plan | 0 | 0
218 | On day two of PI Planning, management presents adjustments based on the previous day's management review and problem-solving meeting. What is one possible type of adjustment they could make? | Redefine the length of the PI Change a team's plan Adjust business priorities Create new User Stories | Adjust business priorities | 0 | 0
219 | What is one approach to unlock the intrinsic motivation of knowledge workers? | Provide autonomy WIP) (Reduce work in process [WIP] limits Centralize decision-making Strive to achieve a state of continuous flow | Provide autonomy | 0 | 0
220 | How does SAFe provide a second operating system that enables Business Agility? | By organizing around functional areas to focus on skills development By focusing on customers, products, innovation, and growth By achieving economies of scale By creating a hierarchy to provide stability Focus on customers/products | Focus on customers/products | 0 | 0
221 | What is one of the inputs to the Portfolio canvas? | Enterprise strategy Value Stream budgets Strategic Themes Portfolio Epics | Strategic Themes | 0 | 0
222 | What is a quality of an Agile team? | Each team has a Scrum Master/Team Coach and a Product Manager Managers direct their work Composed of 10 to 20 members Cross-functional | Cross-functional | 0 | 0
223 | Turn mistakes into learning moments, create a trust-based environment, and visualize work are examples of which SAFe Core Value? | Alignment Transparency Relentless Improvement Respect for People | Transparency | 0 | 0
224 | Which statement is true about uncommitted objectives? | They do not get assigned a business value score They are extra things the team can do if they have time They help improve predictability The work to deliver uncommitted objectives is not planned into the Iterations during PI planning | They help improve predictability | 0 | 0
225 | Which core competency of the Lean Enterprise helps drive Agile Quality practices? | Lean Portfolio Management DevOps and Release on Demand Lean Systems Engineering Team and Technical Agility | Team and Technical Agility | 0 | 0
226 | What makes value available when it's needed? | Infrastructure Release on Demand DevOps Continuous Deployment | Release on Demand | 0 | 0
227 | Which SAFe Core Value emphasizes creating an environment of psychological safety needed to quickly surface and resolve errors? | Respect for People Relentless Improvement Transparency Alignment | Transparency | 0 | 0
228 | The PO Sync is facilitated by? | The RTE or Product Management The Scrum Master or RTE The Scrum Master or Product Owner The RTE or Product Owner | The RTE or Product Management | 0 | 0
229 | According to SAFe, how many Stories should teams maintain in their backlog? | 2-3 weeks of refined Stories 2-3 months of refined Stories 2-3 PIs of refined Stories 2-3 Iterations of refined Stories | 2-3 Iterations of refined Stories | 0 | 0
230 | Which SAFe principle emphasizes applying complex systems to understand the flow of value and identify opportunities for improvement? | Apply systems thinking Unlock the intrinsic motivation of knowledge workers Assume variability, preserve options Decentralize decision-making | Apply systems thinking | 0 | 0
231 | What is the role of the Product Owner during the Daily Stand-up (Team Sync)? | To facilitate the meeting and keep it on track To address impediments raised by the team To provide feedback on the team's performance To listen to the team's progress and issues | To listen to the team's progress and issues | 0 | 0
232 | At what level of flow the Product Owner mainly intervenes? | ART Flow Team Flow Portfolio Flow Solution Train Flow | Team Flow | 0 | 0
233 | True or false, Are The ART planning boards an input to the Planning Interval (PI) Planning Process that highlights how Product Management plans to accomplish the Vision? | False True | False | 0 | 0
234 | Which SAFe Lean-Agile principle support fast feedback? | Assume variability, preserve options Apply systems thinking Make value flow without interruptions Build incrementally with fast, integrated learning cycles | Build incrementally with fast, integrated learning cycles | 0 | 0
235 | What is one responsibility of Product Manager connecting with the Customer? | Create and communicate a compelling vision Conduct primary and secondary research Apply design thinking Collaborate throughout the value stream | Apply design thinking | 0 | 0
236 | What are two different types of Enabler Stories? | Impediment Exploration Infrastructure Defect Feature | Exploration; Infrastructure | 0 | 0
237 | What is one issue that can occur without DevOps? | Challenges between teams that design functionality and those that test the functionality Challenges between teams that deploy products and those that collect customer feedback Challenges between teams that build Solutions and those who operate the Solutions Challenges between teams that talk with customers daily and those that meet with customers for research | Challenges between teams that build Solutions and those who operate the Solutions | 0 | 0
238 | Which two types of customers define SAFE? (Choose two) | External Customers Business partners Internal Customers Stakeholders | External Customers; Internal Customers | 0 | 0
239 | How does SAFe recommend managing risks during PI Planning? | Mitigate risks during the iteration planning meeting Address risks during ART PI Risks session Escalate all risks to senior management Identify and address risks during the management review session | Address risks during ART PI Risks session | 0 | 0
240 | What is the purpose of an Epic Hypothesis Statement? | It helps to capture, organize, and communicate critical information about an epic. It provides enough detail to run the business and keep long-term commitments from interfering with changing business priorities It helps define the pipeline with the assets and technologies needed to deliver solution value It defines an idea that can be validated using the plan, do, check, and adjust cycle | It helps to capture, organize, and communicate critical information about an epic. | 0 | 0
241 | How frequently should the ART Backlog be reviewed? | Continuously When the Epic owners are defining the Epic Value Statement Before every PI Every week | Continuously | 0 | 0
242 | Which model is used in SAFe to prioritize the ART Backlog elements? | MoSCoW Weighted Shortest Job First (WSJF) Value-based prioritization Impact mapping | Weighted Shortest Job First (WSJF) | 0 | 0
243 | What is the main value of the Iteration Planning? | Team prepares requirements for Iteration Planning Team commits to a set of goals to be delivered in the Iteration Team reviews and improves its process before the next Iteration Team meets with stakeholders to review the deliverables and provide feedback | Team commits to a set of goals to be delivered in the Iteration | 0 | 0
244 | What is NOT the role of Product Manager in Exploring Markets and Users? | Identify market rhythms and events understand end-user needs Involve the customer continuously Conduct primary and secondary research | Involve the customer continuously | 0 | 0
245 | Which of the following SAFe events supports Agile Teams to measure the outcome of the Iteration? | The Team Retrospective The Team Sync The Iteration review The PI System Demo | The Iteration review | 0 | 0
246 | What is one way Kanbans are used in SAFe? | To manage runway cadence To manage nonfunctional requirements (NFRs) in the backlog To manage Planning Interval (PI) Objectives To manage queue length | To manage queue length | 0 | 0
247 | According to SAFe, what is one Iteration Retrospective anti-pattern? | The team only brings up issues that are outside of their control to address The team only shares issues that are too small to result in real improvement The team only shares issues that cannot be measured The team only shares issues that are too big to be solved | The team only brings up issues that are outside of their control to address | 0 | 0
248 | What is the primary job of Product Management when considering the Architectural Runway? | Adding Enablers to the Solution roadmap Ensuring sufficient capacity is allocated to Enablers Prioritizing Enablers using weighted shortest job first (WSJF) Writing the Enabler Lean Business case | Ensuring sufficient capacity is allocated to Enablers | 0 | 0
249 | During PI planning, the Product Manager is expected to present the Vision to the Agile Release Train (ART). Which artifact should the Product Manager use to effectively communicate the Vision? | Solution Vision ART Kanban Board Product Roadmap Business Model Canvas | Solution Vision | 0 | 0
250 | What are the four activities of Release on Demand? | Inspect - Adapt- Stabilize and Operate - Learn Learn - Adapt - Stabilize and Operate - Measure Inspect - Measure - Adapt - Release Release - Stabilize and Operate - Measure - Learn | Release - Stabilize and Operate - Measure - Learn | 0 | 0
251 | Why would Product Owners and Product Managers be key collaborators in the enterprise? | They provide governance and spending practices for the value streams They plan Portfolio strategy horizons for the enterprise They plan all the key events for the Planning Interval (PI) They are key roles in steering and sequencing the Agile Release Train priorities | They are key roles in steering and sequencing the Agile Release Train priorities | 0 | 0
252 | What is one Agile development value? | Working teams over busy individuals Healthy interactions over detailed plans Customer collaboration over contract negotiation Risk-taking over process development | Customer collaboration over contract negotiation | 0 | 0
253 | What is the primary focus of an Operational Value Stream? | Improving business operations Lowering operational costs Delivering end-user value Orchestrating supply chain networks | Delivering end-user value | 0 | 0
254 | What is one step determining initial team capacity during PI planning? | Subtract one point for every team member's vacation day, public holiday, or training day Compare final team capacity across all teams Ensure Product Owner/Product Manager approval for all time-based capacity adjustments Add together all of the points from recently completed Features | Subtract one point for every team member's vacation day, public holiday, or training day | 0 | 0
255 | Which increment is reviewed at the System Demo? | Value stream increment Portfolio increment Team increment Full system increment | Full system increment | 0 | 0
256 | What increases the effectiveness of System Demos? | Spend a lot of time preparing for the demo Limit team attendance to minimize disruptions to the team Focus on team-level Metrics Consider how and what to demo during Iteration Planning | Consider how and what to demo during Iteration Planning | 0 | 0
257 | In SAFe work item hierarchy, Features are decomposed into what? | Spikes Enablers Stories Tasks | Stories | 0 | 0
258 | Product Management is involved in the assessment of metrics including the evaluation of business value achieved versus plan. They are also active participants in what else? | Daily Stand-ups (Team Sync) The Inspect and Adapt event Lean budget establishment Team Retrospectives | The Inspect and Adapt event | 0 | 0
259 | ART PI Objectives are : | The synthesis of Business Owners PI Objectives choice The synthesis of the RTE's PI objectives choice The synthesis of each team’s PI Objectives The synthesis of POs/PMs's PI Objectives | The synthesis of each team’s PI Objectives | 0 | 0
260 | What is one important task when communicating the Vision? | Explain the importance of Lean budget Guardrails Communicate the top 10 Features to the ART Verify the capacity allocation Provide user personas to illustrate how the Vision improves the experiences of your Customers | Provide user personas to illustrate how the Vision improves the experiences of your Customers | 0 | 0
261 | Which SAFe core value emphasizes the importance of Providing time and space for innovation? | Alignment Relentless Improvement Respect for People Transparency | Relentless Improvement | 0 | 0
262 | What is a pattern for splitting Features into Stories? | Team skills Tasks to complete Variations in data Layers of the technology stack | Variations in data | 0 | 0
263 | What is one strategy in SAFe 6 for managing Bottlenecks challenges? | Distribute work to other teams Adjust work between teams or split Features and Stories Adjust work between teams based on forecasted capacity Adjust work sequencing to eliminate same Iteration dependencies | Distribute work to other teams | 0 | 0
264 | The customer is asking for a forecast for when a specific Feature will be available for release at the beginning of the next fiscal year. Where could the Product Manager find this information? | System Architecture Designs Development Manager Solution Roadmap ART Backlog | Solution Roadmap | 0 | 0
265 | What is one value of holding regular system demos? | Bottlenecks can be identified early by the teams Execution can be measured across the whole ART Deliverables are reviewed with stakeholders Problems can be escalated to ART leadership | Deliverables are reviewed with stakeholders | 0 | 0
266 | What can increase the effectiveness of Backlog Refinement? | Refine Stories during Iteration Planning Have separate meetings with subject matter experts Include a few team members Schedule the event on a regular cadence | Schedule the event on a regular cadence | 0 | 0
267 | What is one way uncommitted objectives help Agile Teams make a plan for the PI? | They create an opportunity for teams to take on harder work They generate additional ways to measure team progress They ensure the team has additional development options They help improve the predictability of delivering business value | They help improve the predictability of delivering business value | 0 | 0
268 | What are two examples of team-level events? | Team Sync Backlog refinement System demo Coach Sync Planning Interval (PI) Planning | Team Sync; Backlog refinement | 0 | 0
269 | What is the goal of Lean thinking? | Best quality and value for people and society and make business better Relentless improvement Alignment Respect for people | Best quality and value for people and society and make business better | 0 | 0
270 | What is one anti-pattern that emerges when teams do not spend enough time refining the backlog? | Teams arrive to Team Sync without progress to share Teams enter retrospectives without improvement ideas Teams enter new Iterations without enough Stories prepared Teams arrive to Iteration Planning without specified goals | Teams enter new Iterations without enough Stories prepared | 0 | 0
271 | What is the true statement about Market rhythms? | Market rhythms require short-term planning Market rhythms are typically represented on the roadmap as milestones Market rhythms are ad-hoc and often unpredictable Market rhythms are cyclical and predictable | Market rhythms are cyclical and predictable | 0 | 0
272 | Which role does Product Owner work with to prioritize Enablers for the Team Backlog? | System Architect Product Manager Development Team Solution management | System Architect | 0 | 0
273 | During which of the following Agile Team events do team members estimate relative story size? | Iteration Planning Iteration Review Iteration Retrospective Backlog Refinement | Iteration Planning | 0 | 0
274 | What is one activity an Agile Team performs during Iteration Review? | Gather Feature requirements from stakeholders Modify Iteration Goals Demonstrate a working, tested team increment Identify opportunities for improvement | Demonstrate a working, tested team increment | 0 | 0
275 | To calculate WSJF, what teams need to estimate? | Business value and duration Job size and duration Cost of delay and duration Risk reduction and job size | Cost of delay and duration | 0 | 0
276 | According to SAFe, what is one output of a successful Iteration Retrospective? | Improvement Stories Updated ART metrics Updated dependencies between Stories Iteration Goals | Improvement Stories | 0 | 0
277 | What is a pattern for splitting Features into Stories? | Team skills Layers of the technology stack Use case scenarios Tasks to complete | Use case scenarios | 0 | 0
278 | Which SAFe principle emphasize reducing delays, improving product development flow and enabling faster feedback? | Organize around value Assume variability, preserve options Apply systems thinking Decentralize decision-making | Decentralize decision-making | 0 | 0
279 | According to SAFe, which of the following metrics are reported at the Inspect and Adapt event? | ART cycle velocity ART predictability measure Cumulative value measure Cumulative value rate | ART predictability measure | 0 | 0
280 | Acceptance criteria are testable with which syntax? | Given-When-So When-Given-Then Given-When-Then Given-When-Than | Given-When-Then | 0 | 0
281 | Which statement describes an owned ART PI Risk? | There is a strategy to adjust the plan as necessary The risk has been addressed and is no longer a concern Nothing more can be done, so if a risk occurs, release may be compromised Someone has taken the responsibility of the risk | Someone has taken the responsibility of the risk | 0 | 0
282 | What is one way to ensure a team is holding successful Iteration Reviews and demos? | The team shares improving metrics The team swarms to prepare for demos The team ensures they complete every Story The team demos working functionality | The team demos working functionality | 0 | 0
283 | What is the first step of the problem-solving workshop? | Identify the biggest root cause Agree on the problem to solve Restate the new problem for the biggest root cause Perform a root-cause analysis | Agree on the problem to solve | 0 | 0
284 | Which statement describes a resolved ART PI Risk? | Nothing more can be done, so if a risk occurs, release may be compromised Someone has taken the responsibility of the risk The risk has been addressed and is no longer a concern There is a strategy to adjust the plan as necessary | The risk has been addressed and is no longer a concern | 0 | 0
285 | Which Product Owner responsibility helps managing and prioritizing Team Backlog? | Fostering Built-in Quality Supporting the Architectural Runway Testing benefit hypotheses Understanding market forces | Supporting the Architectural Runway | 0 | 0
286 | Product Managers are expected to collaborate in PI Planning the amount of upcoming Enabler work by establishing what? | Capacity allocation Completed Epic acceptance criteria Team Backlog prioritization Accurate user story sizing | Capacity allocation | 0 | 0
287 | What decreases the effectiveness of System Demos? | Team members are not invited to the System Demo to save time Different team members have the opportunity to demo Consider how and what to demo in Iteration Planning The right participants are present | Team members are not invited to the System Demo to save time | 0 | 0
288 | What is one method creates a compelling reason to buy? | Whole-product thinking Persona development Feature storming Journey mapping | Whole-product thinking | 0 | 0
289 | What is the intended value of the Backlog Refinement event? | The team reviews and improves processes before the next Iteration The team is able to prepare requirements for Iteration Planning The team aligns on the progress of Iteration Goals The team is able to commit to a set of goals to be delivered in the Iteration | The team is able to prepare requirements for Iteration Planning | 0 | 0
290 | What is the last activity in Continuous Integration of SAFe's Continuous Delivery Pipeline? | Develop Stage Test end-to-end Build | Stage | 0 | 0
291 | How can teams use Iteration planning to stay aligned on their work? | By reviewing its processes before the next iteration By committing to a set of goals to be delivered By agreeing on a meeting timebox By sharing Stories that could be pairing opportunities | By committing to a set of goals to be delivered | 0 | 0
292 | What is one strategy in SAFe 6 for managing unbalanced teams challenge? | Adjust work between teams or split Features and Stories Distribute work to other teams Adjust work between teams based on forecasted capacity Allocate work between teams based on forcasted capacity | Adjust work between teams based on forecasted capacity | 0 | 0
293 | The definition of done requires that the Story, Satisfies the acceptance criteria and? | Is accepted by the Product Owner Satisfies the end-to-end testing Is accepted by the development team Is accepted by the Product Managers | Is accepted by the Product Owner | 0 | 0
294 | What is one tip for writing effective PI Objectives? | Identifying significant risks Listing out committed Features Remove jargon so that PI Objectives are understandable to Business Owners and Customers Use Features or Stories as PI Objectives | Remove jargon so that PI Objectives are understandable to Business Owners and Customers | 0 | 0
295 | In the INVEST model for story writing, what does S mean? | solidly built Strong solidly explained Small | Small | 0 | 0
296 | What is one method helps understand Customers better? | Journey mapping Whole-product thinking Personas Feature storming | Personas | 0 | 0
297 | What is a PI Planning input that demonstrates how Product Management plans to accomplish the Vision? | The top ten Features The Team Backlog The ART planning boards The business context | The top ten Features | 0 | 0
298 | During the PI Planning, Who owns Feature priorities? | Scrum Masters RTE (Release Train Engineer) Product Management Product Owner | Product Management | 0 | 0
299 | What is one area of area of responsibility of the Product Owner? | Defining Product Strategy Exploring Markets and Users Managing and Prioritizing the ART Backlog Supporting the Team in Delivering Value | Supporting the Team in Delivering Value | 0 | 0
300 | What represents the series of steps an organization uses to deliver a product or service to a Customer? | Capability Value Stream Epic Solution | Value Stream | 0 | 0
301 | What is one question that helps Product Management create a Vision? | What Features and benefit hypotheses do we think it provides? How many Features have been released to the Customer? What are the teams' skills? Which themes are on the Roadmap? | What Features and benefit hypotheses do we think it provides? | 0 | 0
302 | What is Market value consideration when assigning business value? | Functionality that differentiates the product/service from competing products/services and new functionality needed to stay competitive Product/service functionality that brings new revenue or maintains existing revenue Functionality that reduces operating costs, including technical debt or improvements in the pipeline Functionality that focuses on enabling or realizing future value, including Enablers, proofs of concept (POCs), and research spikes | Functionality that differentiates the product/service from competing products/services and new functionality needed to stay competitive | 0 | 0
303 | What purpose do Iteration Goals serve? | Delving too deep into technical discussions Help the team finalize all User Stories Align teams to common PI Objectives and manage dependencies Bringing Stories that haven’t been refined and prioritized | Align teams to common PI Objectives and manage dependencies | 0 | 0
304 | Team Tigers has decided to use the IP Iteration to continue the finalizing Feature delivery work they have been working on for the past two Iterations. What is one effect Team Tigers might experience by continuing to stay heads-down rather than using the IP Iteration as intended? | Individual team members could lose an opportunity to consider their team work more holistically Individual team members could lose an opportunity to learn from one another Individual team members could lose an opportunity to refresh their motivation Individual team members could lose an opportunity to keep their technical skills current | Individual team members could lose an opportunity to keep their technical skills current | 0 | 0
305 | What is one potential root cause of Team Sync anti-patterns? | Occasional conflict within the team Communication between team members Frequent verification and integration during the Iteration Lack of collective ownership | Lack of collective ownership | 0 | 0
306 | Which role creates the Vision for the ART? | Product Management RTE Business Owners Product Owner | Product Management | 0 | 0
307 | Which of the following statements is one of the five Lean Thinking principles? | Let the Customer pull value from the producer customer collaboration over contract negotiation Assume variability, preserve options Deliver working software frequently | Let the Customer pull value from the producer | 0 | 0
308 | What can Product managers use to quickly estimate the size of Features in Story points? | Affinity Mapping Historical data Ideal Days T-Shirt Sizing | Historical data | 0 | 0
309 | Which two aspects of the Continuous Delivery Pipeline require the most involvement from Product Management? | Continuous Integration and Release on Demand Continuous Exploration and Continuous Deployment Continuous Exploration and Release on Demand Continuous Integration and Continuous Deployment | Continuous Exploration and Release on Demand | 0 | 0
310 | Which of the following roles has design authority for the ART Backlog? | Business Owner The System Architect The RTE The Product Management | The System Architect | 0 | 0
311 | What unit of time is used on PI Roadmaps? | Years Iterations PIs Months | PIs | 0 | 0
312 | Which of the following events provides an opportunity to assess scope adjustments? | Iteration Planning Backlog Refinement Inspect and Adapt PO Sync | PO Sync | 0 | 0
313 | What helps Getting to production early? | Understand Customer needs Continuous Deployment Continuous Integration Feature Toggle | Continuous Deployment | 0 | 0
314 | What is the recommended duration by SAFe for System Demo? | 2 Hours 1 Hour 3 Hours As needed | 1 Hour | 0 | 0
315 | What is the recommended Timebox by SAFe for Backlog Refinement? | As needed 2 Hours 1 Hour 3 Hours | 1 Hour | 0 | 0
316 | Which of the following is the primary focus of Lean Portfolio Management? | Define the enterprise strategy Establish lean budgets Align strategy and execution Ensure program and portfolio execution | Define the enterprise strategy Establish lean budgets Align strategy and execution Ensure program and portfolio execution | 0 | 0
317 | What is the primary purpose of Strategic Themes? | Determine the order in which Epics should be executed Drive incremental implementation across the enterprise Define the sequence of steps used to deliver value to the customer Connect the portfolio to the enterprise business strategy | Determine the order in which Epics should be executed Drive incremental implementation across the enterprise Define the sequence of steps used to deliver value to the customer Connect the portfolio to the enterprise business strategy | 0 | 0
318 | What is one fundamental difference between Agile Software Engineering and Waterfall? | Agile delivers every single requested requirement. Waterfall has no fixed schedule. Agile supports test-first development. Waterfall concentrates on code quality. | Agile supports test-first development. | 0 | 0
319 | What is the purpose of having deployment decoupled from release? | To enable deploying upon demand. To remove the need to respond quickly to product issues. To enable releasing upon demand. To make deploying a business decision. | To enable releasing upon demand. | 0 | 0
320 | Which of the following is a Lean Budget Guardrail? | Participatory budgeting Investment horizons Centralized decision-making Lean startup cycle | Participatory budgeting Investment horizons Centralized decision-making Lean startup cycle | 0 | 0
321 | What is BDD? | Business-Driven Development Benchmark-Driven Development Behavior-Driven Development Backlog-Driven Development | Business-Driven Development Benchmark-Driven Development Behavior-Driven Development Backlog-Driven Development | 0 | 0
322 | Which two actions can slow the delivery of value? | Shortened Architectural Runway Loopbacks System delays Team swarming | Shortened Architectural Runway Loopbacks System delays Team swarming; Shortened Architectural Runway Loopbacks System delays Team swarming | 0 | 0
323 | Which two statements best describe a cross-functional Agile Team? | They are optimized for communication and delivery of value. They can define, build, and test a Feature or component. They deliver value every six weeks. They release customer products to production continuously. They are made up of members, each of whom can define, develop, test, and deploy the system. | They are optimized for communication and delivery of value.; They can define, build, and test a Feature or component. | 0 | 0
324 | The role of the Product Manager is most similar to what other role in SAFe? | Development Manager Solution Manager Release Train Engineer Business Manager | Development Manager Solution Manager Release Train Engineer Business Manager | 0 | 0
325 | What is the foundation of Lean? | Innovation Lean-Agile development Leadership Lean-thinking | Innovation Lean-Agile development Leadership Lean-thinking | 0 | 0
326 | What is a benefit of continuously deploying using a DevOps model? | It alleviates the reliance on the skill sets of Agile Teams. It ensures that changes deployed to production are always immediately available to end-users. It lessens the severity and frequency of release failures. It increases the transaction cost. | It lessens the severity and frequency of release failures. | 0 | 0
327 | What are three practices for building large Solutions? | Employ and improve the Continuous Development Pipeline. Employ multiple Solution Teams. Build Solution components and capabilities with ARTs. Build and integrate the Solution with a Solution Train. Ensure value stream consistency. Capture and refine system specifications as fixed/variable Solution Intent. | Build and integrate the Solution with a Solution Train.; Build Solution components and capabilities with ARTs.; Capture and refine system specifications as fixed/variable Solution Intent. | 0 | 0
328 | What is the ultimate goal of DevOps in SAFe? | To enable Agile Release Trains to deliver value more frequently. To combine Development and Operations groups into one team. To clarify program and team roles. To automate the integration, testing, and deployment of features. | To enable Agile Release Trains to deliver value more frequently. | 0 | 0
329 | In which event are the PI Objectives created? | Post PI-Planning PI Planning Iteration Planning PI System Demo | Post PI-Planning PI Planning Iteration Planning PI System Demo | 0 | 0
330 | Which statement is most accurate about the Solution Vision? | It summarizes the team PI Objectives for the current Program Increment. It provides an outline of the Features for the next three Program Increments. It expresses the strategic intent of the Program. It drives the allocation of budget for the Agile Release Train. | It expresses the strategic intent of the Program. | 0 | 0
331 | What does Solution Intent describe? | The customer or consumer of the solution. The behavior of the solution. The platform architecture. Where the solution operates. | The behavior of the solution. | 0 | 0
332 | Which of the following is a key purpose of DevOps? | DevOps joins development and operations to enable continuous delivery. DevOps focuses on automating the delivery pipeline to reduce transaction cost. DevOps enables continuous release by building a scalable Continuous Delivery Pipeline. DevOps focuses on a set of practices applied to large systems. | DevOps joins development and operations to enable continuous delivery. | 0 | 0
333 | What is the purpose of dynamic models? | They are used when there are numerous and complex interactions. They are used when there are a set of parallel interactions related to a scenario. They are used when there are a specific number of interactions that are less complex. They are used to sequence a set of interactions related to a scenario. | They are used when there are numerous and complex interactions. | 0 | 0
334 | At what level of the SAFe Big Picture do Strategic Themes reside? | Essential Level. Team Level. Portfolio Level. Large Solution Level. | Portfolio Level | 0 | 0
335 | Which of the following is responsible for managing the Portfolio Kanban? | Lean Portfolio Management. Release Train Engineer. Product Management. Solution Management. | Lean Portfolio Management | 0 | 0